## Config (hidden)
WorkCentres | Stations | Priorities | Statuses
Profiling | Profiling | Urgent | Not Started
Saw | Saw | High | In Progress
Machining | Machining 1 | Normal | On Hold
Fabrication | Machining 2 | Low | Complete
Weld | Fabrication 1 |  | Waiting Materials
Blast | Fabrication 2
Paint | Weld 1
Assembly | Weld 2
Weld 3
Blast
Paint
Assembly 1
Assembly 2

## Master Schedule
PRODUCTION SCHEDULE
Agricultural Machinery Manufacturer — Live Job Tracker
JOB IDENTITY | [11 empty] | PROFILING |  |  |  | SAW |  |  |  | MACHINING 1 |  |  |  | MACHINING 2 |  |  |  | FABRICATION 1 |  |  |  | FABRICATION 2 |  |  |  | WELD 1 |  |  |  | WELD 2 |  |  |  | WELD 3 |  |  |  | BLAST |  |  |  | PAINT |  |  |  | ASSEMBLY 1 |  |  |  | ASSEMBLY 2
Job ID | Customer | Product/Description | Order Qty | Drawing Ref | Job Priority | Overall Status | Order Due Date | Date Received | Days Until Due | Priority Rank | Notes | Profiling Status | Profiling Est Hrs | Profiling Operator | Profiling Notes | Saw Status | Saw Est Hrs | Saw Operator | Saw Notes | Machining 1 Status | Machining 1 Est Hrs | Machining 1 Operator | Machining 1 Notes | Machining 2 Status | Machining 2 Est Hrs | Machining 2 Operator | Machining 2 Notes | Fabrication 1 Status | Fabrication 1 Est Hrs | Fabrication 1 Operator | Fabrication 1 Notes | Fabrication 2 Status | Fabrication 2 Est Hrs | Fabrication 2 Operator | Fabrication 2 Notes | Weld 1 Status | Weld 1 Est Hrs | Weld 1 Operator | Weld 1 Notes | Weld 2 Status | Weld 2 Est Hrs | Weld 2 Operator | Weld 2 Notes | Weld 3 Status | Weld 3 Est Hrs | Weld 3 Operator | Weld 3 Notes | Blast Status | Blast Est Hrs | Blast Operator | Blast Notes | Paint Status | Paint Est Hrs | Paint Operator | Paint Notes | Assembly 1 Status | Assembly 1 Est Hrs | Assembly 1 Operator | Assembly 1 Notes | Assembly 2 Status | Assembly 2 Est Hrs | Assembly 2 Operator | Assembly 2 Notes
J-1001 | Brennan Agri Ltd | Disc Harrow 3m | 5 | DH-3000 | Urgent | In Progress | 2026-02-16 | 2026-01-22 |  |  |  | Complete | 2 | Tom B. |  | Complete | 1.5 | Tom B. |  | Complete | 4 | Kevin D. |  | Not Started | 4 |  |  | In Progress | 6 | Declan O. |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1002 | Murphy Farms | Muck Spreader 6T | 2 | MS-6000 | High | In Progress | 2026-02-19 | 2026-01-27 |  |  |  | Complete | 2 | Tom B. |  | Complete | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Complete | 6 | Declan O. |  | In Progress | 6 | Declan O. |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1003 | O'Brien Tillage | Subsoiler 5-Leg | 3 | SS-0500 | Urgent | In Progress | 2026-02-13 | 2026-01-12 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Tom B. |  | Complete | 4 | Pat M. |  | Complete | 4 | Pat M. |  | Complete | 6 | Declan O. |  | Not Started | 6 |  |  | In Progress | 8 | Ciaran W. |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1004 | Kelly Contracting | Bale Handler Twin | 4 | BH-2000 | High | In Progress | 2026-02-23 | 2026-02-01 |  |  |  | Complete | 2 | Tom B. |  | Complete | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Complete | 6 | Brian S. |  | Not Started | 6 |  |  | Complete | 8 | Ciaran W. |  | In Progress | 8 | Dave L. |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1005 | Walsh Plant Hire | Roller Cambridge 4m | 1 | RC-4000 | Normal | In Progress | 2026-02-28 | 2026-02-06 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | In Progress | 6 | Declan O. |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1006 | Fitzpatrick Agri | Trailer 14T Grain | 2 | TG-1400 | Normal | Not Started | 2026-03-07 | 2026-02-11 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1007 | Connolly & Sons | Disc Harrow 4m | 3 | DH-4000 | High | In Progress | 2026-02-22 | 2026-02-03 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Liam F. |  | In Progress | 4 | Kevin D. |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1008 | Riordan Farm Supplies | Muck Spreader 8T | 1 | MS-8000 | Low | Not Started | 2026-03-14 | 2026-02-16 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1009 | Daly Agri Repairs | Subsoiler 7-Leg | 2 | SS-0700 | Normal | In Progress | 2026-02-24 | 2026-01-30 |  |  |  | Complete | 2 | Tom B. |  | In Progress | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1010 | Burke Plant | Bale Handler Single | 6 | BH-1000 | Urgent | In Progress | 2026-02-18 | 2026-01-17 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Complete | 6 | Declan O. |  | Not Started | 6 |  |  | Complete | 8 | Eoin P. |  | Complete | 8 | Ciaran W. |  | Not Started | 8 |  |  | In Progress | 2 | Alan F. |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1011 | Healy Farms | Roller Flat 3m | 2 | RF-3000 | Normal | Not Started | 2026-03-03 | 2026-02-09 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1012 | Sheehan Contracting | Trailer 10T Grain | 3 | TG-1000 | High | In Progress | 2026-02-21 | 2026-01-24 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Liam F. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Complete | 6 | Declan O. |  | Complete | 6 | Mark T. |  | Complete | 8 | Ciaran W. |  | In Progress | 8 | Dave L. |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1013 | O'Sullivan Plant Hire | Disc Harrow 5m | 2 | DH-5000 | Low | Not Started | 2026-03-23 | 2026-02-18 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1014 | Cronin Agri | Muck Spreader 10T | 1 | MS-A000 | High | Waiting Materials | 2026-02-23 | 2026-02-01 |  |  |  | Waiting Materials | 2 | Tom B. |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1015 | McCarthy Farm Equip | Subsoiler 3-Leg | 4 | SS-0300 | Normal | Not Started | 2026-03-11 | 2026-02-13 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1016 | Power Agri Ltd | Bale Handler Triple | 2 | BH-3000 | Urgent | In Progress | 2026-02-20 | 2026-01-07 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Liam F. |  | Complete | 4 | Pat M. |  | Complete | 4 | Pat M. |  | Complete | 6 | Declan O. |  | Complete | 6 | Declan O. |  | Complete | 8 | Eoin P. |  | Complete | 8 | Ciaran W. |  | Complete | 8 | Shane C. |  | Complete | 2 | Paul G. |  | In Progress | 3 | Ger M. |  | Not Started | 5 |  |  | Not Started | 5
J-1017 | Nolan Plant | Roller Cambridge 6m | 1 | RC-6000 | Normal | Not Started | 2026-03-18 | 2026-02-15 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1018 | Treacy Agri Supplies | Trailer 16T Grain | 2 | TG-1600 | High | On Hold | 2026-02-24 | 2026-01-20 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Liam F. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | On Hold | 6 | Brian S. |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1019 | Delaney Farms | Disc Harrow 6m | 1 | DH-6000 | Low | Not Started | 2026-04-07 | 2026-02-19 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1020 | Flynn Contracting | Muck Spreader 4T | 3 | MS-4000 | Normal | In Progress | 2026-02-27 | 2026-02-07 |  |  |  | Complete | 2 | Tom B. |  | In Progress | 1.5 | Liam F. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1021 | Higgins Farm Mach. | Subsoiler 9-Leg | 1 | SS-0900 | High | In Progress | 2026-02-22 | 2026-01-26 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Tom B. |  | Complete | 4 | Kevin D. |  | Not Started | 4 |  |  | In Progress | 6 | Declan O. |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1022 | Egan Plant Hire | Bale Handler Twin XL | 2 | BH-2100 | Normal | Not Started | 2026-03-05 | 2026-02-12 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1023 | Ryan Agri | Roller Flat 5m | 2 | RF-5000 | Urgent | Complete | 2026-02-15 | 2026-01-02 |  |  |  | Complete | 2 | Tom B. |  | Complete | 1.5 | Tom B. |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Complete | 6 | Declan O. |  | Complete | 6 | Mark T. |  | Complete | 8 | Eoin P. |  | Complete | 8 | Dave L. |  | Complete | 8 | Shane C. |  | Complete | 2 | Alan F. |  | Complete | 3 | Paul G. |  | Complete | 5 | Frank D. |  | Complete | 5 | Frank D.
J-1024 | Dooley Farm Supplies | Trailer 8T Silage | 3 | TS-0800 | Low | Not Started | 2026-03-28 | 2026-02-17 |  |  |  | Not Started | 2 |  |  | Not Started | 1.5 |  |  | Not Started | 4 |  |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
J-1025 | Kavanagh Agri Ltd | Disc Harrow 2.5m Folding | 4 | DH-2500 | High | Waiting Materials | 2026-02-23 | 2026-02-04 |  |  |  | Complete | 2 | Sean R. |  | Complete | 1.5 | Liam F. |  | Waiting Materials | 4 | Kevin D. |  | Not Started | 4 |  |  | Not Started | 6 |  |  | Not Started | 6 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 8 |  |  | Not Started | 2 |  |  | Not Started | 3 |  |  | Not Started | 5 |  |  | Not Started | 5
Formulas:
Days Until Due = IFERROR([Order Due Date]-TODAY(),"")

## Dashboard
PRODUCTION DASHBOARD
Manager Overview — Live KPIs
Total Active Jobs |  |  | Overdue Jobs |  |  | Due This Week |  |  | Total Remaining Est Hrs
Station | Jobs Queued | Remaining Hrs | Urgent | High | Normal | Low | Overdue | Due This Week | % Complete
Profiling
Saw
Machining 1
Machining 2
Fabrication 1
Fabrication 2
Weld 1
Weld 2
Weld 3
Blast
Paint
Assembly 1
Assembly 2
TOTAL

## Queue — All
QUEUE — ALL STATIONS
Use dropdowns to filter by Work Centre and Priority
Work Centre: | All | Priority: | All
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Overall Status | Order Due Date | Days Until Due | Assigned Station | Notes

## Queue — Profiling
QUEUE — PROFILING
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Profiling Status | Profiling Est Hrs | Profiling Operator | Profiling Notes

## Queue — Saw
QUEUE — SAW
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Saw Status | Saw Est Hrs | Saw Operator | Saw Notes

## Queue — Machining 1
QUEUE — MACHINING 1
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Machining 1 Status | Machining 1 Est Hrs | Machining 1 Operator | Machining 1 Notes

## Queue — Machining 2
QUEUE — MACHINING 2
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Machining 2 Status | Machining 2 Est Hrs | Machining 2 Operator | Machining 2 Notes

## Queue — Fabrication 1
QUEUE — FABRICATION 1
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Fabrication 1 Status | Fabrication 1 Est Hrs | Fabrication 1 Operator | Fabrication 1 Notes

## Queue — Fabrication 2
QUEUE — FABRICATION 2
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Fabrication 2 Status | Fabrication 2 Est Hrs | Fabrication 2 Operator | Fabrication 2 Notes

## Queue — Weld 1
QUEUE — WELD 1
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Weld 1 Status | Weld 1 Est Hrs | Weld 1 Operator | Weld 1 Notes

## Queue — Weld 2
QUEUE — WELD 2
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Weld 2 Status | Weld 2 Est Hrs | Weld 2 Operator | Weld 2 Notes

## Queue — Weld 3
QUEUE — WELD 3
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Weld 3 Status | Weld 3 Est Hrs | Weld 3 Operator | Weld 3 Notes

## Queue — Blast
QUEUE — BLAST
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Blast Status | Blast Est Hrs | Blast Operator | Blast Notes

## Queue — Paint
QUEUE — PAINT
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Paint Status | Paint Est Hrs | Paint Operator | Paint Notes

## Queue — Assembly 1
QUEUE — ASSEMBLY 1
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Assembly 1 Status | Assembly 1 Est Hrs | Assembly 1 Operator | Assembly 1 Notes

## Queue — Assembly 2
QUEUE — ASSEMBLY 2
Jobs in Queue |  |  | Remaining Hrs |  |  | Overdue |  |  | Urgent
# | Job ID | Customer | Product/Description | Drawing Ref | Job Priority | Order Due Date | Days Until Due | Assembly 2 Status | Assembly 2 Est Hrs | Assembly 2 Operator | Assembly 2 Notes